## Activity Log
Team Name: |  |  | Burrito Buddies Mark 2 Deluxe |  |  | Total Work Time: |  |  | 10.09
Member Name: |  |  | Celeste Miranda |  |  | Development Week: |  |  | Week 7
Task | Light and Audio Change | [7 empty] | ESTIMATED Time in Hours
1 | Looked for ways to change the atmosphere of the overall game. To create a more western theme, the lighting was changed to a more sepia color. It gave the a more orange hue, reminding the player it was a western setting. The main background theme was also changed to reflect the theme. This took a while to find due to copyright reasons. | [7 empty] | 0.75
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 1.33 | 0 | 0 | 0 | 1.33
Task | New UI Border Element | [7 empty] | ESTIMATED Time in Hours
2 | Created a new UI border to surround panels. The UI element is a custome rope in a rectangular shape. The rope fits the overall western theme next to the wood, cowboy hat and wanted paper elements. The colors fit the overall color pallete of browns and dark oranges. The border has a somewhat semetrical feel because one piece of rope was created, then altered in direction for each corner. | [7 empty] | 1
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 1.73 | 0 | 0 | 0 | 0 | 1.73
Task | Designed Player Walk Animation | [7 empty] | ESTIMATED Time in Hours
3 | Gathered the idle player sprites and used them as a guide to create a basic walk animation. Focused on giving the illusion of walking by changing foot direction or visibility. Created individual frames in GIMP for each step. Used Piskel to check animation and re-arrange frames to create a smoother transition. Created a sprite sheet for each direction. | [7 empty] | 3.25
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 4.42 | 0 | 0 | 4.42
Task | Add Walk Animation to the Player Object | [7 empty] | ESTIMATED Time in Hours
4 | Loaded walk spritesheets into Unity. Created an animation file for each spritesheet. Adjusted the sample time to be slower to account for player movement. Played with the already created player animator to determine how to add the new walk animations. Used the idle bool to call the player walk animation. Walk animation is connected to the idle sprites. | [7 empty] | 2
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 0 | 2.61 | 0 | 2.61