## Activity Log
Team Name: |  |  | Burrito Buddies Mark 2 Deluxe |  |  | Total Work Time: |  |  | 7
Member Name: |  |  | David Highsmith |  |  | Development Week: |  |  | 3
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
1 | Download Blender. Create Model for projectile and integrate into the player. Add changes to repository. | [7 empty] | 1
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
2 | Discussed story with Tyler and Basics of art direction. | [7 empty] | 1
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 1
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
3 | Team meetings to disseminate information. | [7 empty] | 1
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 1
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
4 | Explore features in Unity and get used to handling them. | [7 empty] | 2
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2