## Activity Log
Team Name: |  |  | Burrito Buddies |  |  | Total Work Time: |  |  | 22
Member Name: |  |  | David Pittman |  |  | Development Week: |  |  | 5
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
1 | Atempt to implement the grid points for A* for collision detection/navigation. | [7 empty] | 8
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 6
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
2 | Scrap A* in favor of Nav Mesh/Nav Mesh Agent. Add additional cactus/rocks to scene and increase terrain size. Adjusted barriers placment to fit new terrain area. | [7 empty] | 8
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 6
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
3 | Add enemy hit damage and random generate of enemy instances. (this one drove me nuts) | [7 empty] | 8
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8 | 10