## Activity Log
Team Name: |  |  | Burrito Buddies |  |  | Total Work Time: |  |  | 13
Member Name: |  |  | Tyler Purcell |  |  | Development Week: |  |  | 3
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
1 | Design/Create UI Template | [7 empty] | 5+ hours
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 1.5 | 1.5 | 0 | 2 | 0 | 1.5 | 6.5
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
2 | Setup Scene Transition (rough) | [7 empty] | 1+ hours
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
3 | Dealt with Git issuses | [7 empty] | unexpected
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0.5 | 0 | 0 | 0.5 | 0 | 1 | 2
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
3 | Write up documents | [7 empty] | 1+ hours
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4