## Activity Log
Team Name: |  |  | Burrito Buddies Mark 2 Deluxe |  |  | Total Work Time: |  |  | 8
Member Name: |  |  | David Highsmith |  |  | Development Week: |  |  | 5
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
1 | Created ending credits screen. Added credits scrolling script. Located ending credits music. | [7 empty] | 2
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 1 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
2 | Looked for and added sounds to the game. A player death/injury sound, some game over music and an enemy hit sound. | [7 empty] | 1
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1.5
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
3 | Hooked the enemy hit sounds and the player injury sounds into the game. Had trouble with the player injury sounds and had to attempt multiple implimentations to get it to work correctly. | [7 empty] | 2
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
4 | [8 empty] | 0
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0