## Activity Log
Team Name: |  |  | Burrito Buddies Mark 2 Deluxe |  |  | Total Work Time: |  |  | 16.25
Member Name: |  |  | David Pittman |  |  | Development Week: |  |  | 2
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
1 | Review Unity tutorials from Treehouse for indepth functionality and better grasp of game engine. | [7 empty] | 13 hours
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 2 | 2 | 2 | 2 | 6 | 14
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
2 | Assist with team charter and production plan. | [7 empty] | 2
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
3 | Add David Highsmith and Celesete Miranda as collaborators to git repository | [7 empty] | 0.5
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0.25