## Activity Log
Team Name: |  |  | Burrito Buddies Mark 2 Deluxe |  |  | Total Work Time: |  |  | 18
Member Name: |  |  | David Pittman |  |  | Development Week: |  |  | 5
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
1 | Work at building cusom prefabs and especially the animated door prefab. | [7 empty] | 8
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 2 | 2 | 0 | 0 | 0 | 9 | 13
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
2 | Second go at the AI nav mesh. | [7 empty] | 8
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 5
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
3 | [8 empty] | 0
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0