## Activity Log
Team Name: |  |  | Burrito Buddies Mark 2 Deluxe |  |  | Total Work Time: |  |  | 15.1
Member Name: |  |  | Celeste Miranda |  |  | Development Week: |  |  | Week 5
Task | Create Mock Player Sprite | [7 empty] | ESTIMATED Time in Hours
1 | Sketched out several ideas for the player sprite. Unable to solidify any design and had a harder time to think of color palette. Instead, created a quick mock up in GIMP. Sent it to the group and used this as the player sprite. Will continue to determine how to animate the player sprite. | [7 empty] | 3
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0.48 | 0.34 | 0.42 | 0 | 0 | 1.71 | 0 | 2.95
Task | Create UI Elements | [7 empty] | ESTIMATED Time in Hours
2 | Created a few different UI elements. Used GIMP to create the game button; originally had text on it but group decided to remove it. Imported font so group can use it. Got an image of burnt paper and made adjustments to use as the background for the speaker in the dialogue panel. Created a table-like image to use as the background for the text in the dialogue panel. Also created a cowboy hat. | [7 empty] | 3
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 0 | 3.16 | 2.75 | 5.91
Task | Create Dialogue and Status Report | [7 empty] | ESTIMATED Time in Hours
3 | Determined a few Mexican foods that could be used as puns. Used these puns to create several lines of dialogue for the game. Kept dialogue ambigious so it can be used by an enemy or the player. Researched other food related puns but used them to a lesser extent. Determined quality of pun based on other's reactions. Sent the text the group. Started working on the status report as well. | [7 empty] | 1
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0.34 | 0.39 | 0 | 0.52 | 0 | 0.21 | 1.46
Task | Work Out GitHub and Project Issues | [7 empty] | ESTIMATED Time in Hours
4 | GitHub branch that was being worked on was outdated. Had issues trying to update from the master branch. Had to delete and clone project repeatedly. Once the correct project was in, had issues switching branches because it was basing information off outdated information. | [7 empty] | 1.5
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 1.24 | 2.81 | 0.73 | 4.78