## Activity Log
Team Name: |  |  | Burrito Buddies Mark 2 Deluxe |  |  | Total Work Time: |  |  | 10.09
Member Name: |  |  | Celeste Miranda |  |  | Development Week: |  |  | Week 6
Task | Created Hot Sauce Bottle Sprites | [7 empty] | ESTIMATED Time in Hours
1 | Created two sprites for the player's hot sauce bottle. The red one represent regular hot sauce and a brown-ish one to repesent spicy hot sauce. Used GIMP to create sprites. | [7 empty] | 0.5
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 0.53 | 0 | 0 | 0.53
Task | Add Hot Sauce Bottle Sprites and Integration | [7 empty] | ESTIMATED Time in Hours
2 | Added hot sauce bottle sprites to Unity. Created animators and animations for each. Added code to scripts so bottle would spin and be in the correct orientation. Took longer because sprite was not rotating locally or was rotating incorrectly. Had more issues trying to find a solution to update bottle based on power up (which switches to the spicy sprite). Found solution for both. | [7 empty] | 3
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 1.22 | 7.59 | 0 | 8.81
Task | Feedback Forms and Status Report | [7 empty] | ESTIMATED Time in Hours
3 | Used Google Drive to upload a zipped package of Burrito Bandit. The file included the executable and all necessary files. Asked who would be able to participate and shared the files with them. Downloaded sent back feedback and renamed files. Updated status report by comparing group's memebers addition and the Skype chat log. | [7 empty] | 1
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 0.29 | 0 | 0.46 | 0.75
Task | [8 empty] | ESTIMATED Time in Hours
4 | [8 empty] | 0
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0