## Activity Log
Team Name: |  |  | Burrito Buddies |  |  | Total Work Time: |  |  | 11
Member Name: |  |  | David Pittman |  |  | Development Week: |  |  | 3
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
1 | Add basic objects that will later be deformed to make the skeletons, cacti. Increased the scale size of the terrain so the character doesn't fall off the grid. | [7 empty] | 3
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 4
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
2 | Added additional functions to allow player character to move in the direction fo the mouse cursor. | [7 empty] | 2
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
Task | Activity Description (Anticipated Completion Results) | [7 empty] | ESTIMATED Time in Hours
3 | Attempted to merge the codeline for the menu creation. | [7 empty] | 2
| Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Actual Time in Hours
| 0 | 0 | 0 | 0 | 2 | 2 | 2 | 8 | 6