## Master Task List
Master Task List
Task ID | Task Description | Hours | Priority | Dependencies? | Owner | Status
AI001 | Create Enemy AI | Long | Medium |  | David P. | Ongoing
AS001 | Create player character | Medium | High |  | David P., Tyler | Complete
AS001.1 | Improve Quality: player character | Medium | Medium |  | Tyler, Celeste | Complete
AS002 | Implement projectiles | Medium | Medium |  | Tyler | Complete
AS002.1 | Improve Projectile model | Medium | Low |  | David H. | Complete
AS003 | Implement Damageable targets | Medium | Medium |  | David P., Tyler | Complete
AS004 | Implement Power Ups | Medium | Medium |  | Tyler | Complete
AS004.1 | Improve Power Up model | Medium | Low |  | David H. | Complete
AS005 | Implement Sounds | Medium | Medium |  | Tyler | Complete
AS005.1 | create/import various needed Sound assests | Medium | Medium |  | David H. | Complete
AS005.2 | Implement various needed Sound assests | Medium | Medium |  | David H., David P., Tyler | Complete
AS006 | Implement rocks assest | Medium | Medium |  | Tyler | Complete
AS007 | Implement cactus assest | Medium | Medium |  | Tyler | Complete
AS008 | Implement Entity Spawner | Medium | Medium |  | David P., Tyler | Complete
AS008.1 | Improve Entity Spawner (tooltip, room vs player, bounds limitations.) | Long | Medium |  | Tyler | Ongoing
AS009 | Build base 2D sprite billboard entity template | Medium | High |  | Tyler | Complete
AS010 | Create Burrito Mob Sprite Animations | Medium | High |  | Celeste | Complete
AS011 | Create WHACK-amole : a guacamole mole. | Medium | Medium | SB003 | Celeste | Complete
BE001 | Add failure sequence | Medium | Medium |  | Tyler | Complete
BE002 | Boss encounter sequence | Medium | Medium |  |  | Ongoing
BE003 | Saving High score | Medium | Low |  | Tyler | Complete
BE004 | Auto-save high score | Medium | Low |  | Tyler | Complete
BE005 | Implement Nav mesh | Medium | Medium |  | David P., Tyler | Complete
LD001 | Create experimental level | Medium | High |  | David P., Tyler | Complete
LD002 | Create first level | Medium | High | SB001 |  | Ongoing
LD003 | Create secound level | Medium | High | SB001
LD004 | Create third level | Medium | High | SB001
IN001 | Establish a repository | Quick | Critical |  | David P., Tyler | Complete
IN002 | Create and Share Unity Project (thru repository) | Quick | Critical |  | David P. | Complete
RD001 | Research potential premade assets | Long | Medium |  | All | Ongoing
RD002 | Review game mechanics (make changes, etc.) | Medium | Medium |  | All | Ongoing
SB001 | Work out story / plot | Medium | High |  | All | Ongoing
SB002 | Write up dialog | Medium/Long | Medium | SB001 | All | Ongoing
SB003 | Draw up Character mockups | Medium/Long | High |  | Celeste | Complete
UI001 | Create Main Menu | Medium | High |  | Tyler | Complete
UI001.1 | Improve Quality: Main Menu | Medium | Low |  | Tyler, Celeste | Complete
UI002 | Create In Game pause menu | Medium | Medium |  | Tyler | Complete
UI002.1 | Improve Quality: In Game pause menu | Medium | Low |  | Tyler, Celeste | Complete
UI003 | Create HUD (health / score) | Medium | Medium |  | Tyler | Complete
UI003.1 | Improve Quality: HUD (health / score) | Medium | Low |  | Tyler | Complete
UI004 | Setup Player Controls | Medium | Medium |  | Tyler | Complete
UI005 | Add Options | Medium | Low |  | Tyler | Complete
UI005.1 | Add Additional options | Low | Low
UI006 | Level Transition | Medium | Medium |  | Tyler | Ongoing
UI007 | End Game Sequence / Credits | Medium | Low |  | David H., Tyler, Celeste | Complete
UI008 | Implement Dialog Pop ups | Medium | Medium |  | Tyler | Complete

## Session 1 Schedule
Weekly Task Schedule for Session 1
Week 2
Owner | Task Description | Task ID | Duration | Dependencies?
Week 3
Owner | Task Description | Task ID | Duration | Dependencies?
Week 4
Owner | Task Description | Task ID | Duration | Dependencies?
Week 5
Owner | Task Description | Task ID | Duration | Dependencies?
Week 6
Owner | Task Description | Task ID | Duration | Dependencies?
Week 7
Owner | Task Description | Task ID | Duration | Dependencies?
Week 8
Owner | Task Description | Task ID | Duration | Dependencies?

## Session 2 Schedule
Weekly Task Schedule for Session 2
Week 2
Owner | Task Description | Task ID | Duration | Dependencies?
Week 3
Owner | Task Description | Task ID | Duration | Dependencies?
Week 4
Owner | Task Description | Task ID | Duration | Dependencies?
David P. | Create Enemy AI | AI001 | Long
David H. | Improve Projectile model | AS002.1 | Medium
David H. | Improve Power Up model | AS004.1 | Medium
David H. | create/import various needed Sound assests | AS005.1 | Medium
Tyler | Improve Entity Spawner (tooltip, room vs player, bounds limitations.) | AS008.1 | Long
Tyler | Build base 2D sprite billboard entity template | AS009 | Medium
Celeste | Create Burrito Mob Sprite Animations | AS010 | Medium
Celeste | Create WHACK-amole : a guacamole mole. | AS011 | Medium | SB003
All | Research potential premade assets | RD001 | Long
All | Review game mechanics (make changes, etc.) | RD002 | Medium
Tyler | Improve Quality: In Game pause menu | UI002.1 | Medium
Tyler | Improve Quality: HUD (health / score) | UI003.1 | Medium
Tyler | Level Transition | UI006 | Medium
All | Write up dialog | SB002 | Medium/Long | SB001
Celeste | Draw up Character mockups | SB003 | Medium/Long
David H. | End Game Sequence / Credits | UI007 | Medium
Week 5
Owner | Task Description | Task ID | Duration | Dependencies?
Week 6
Owner | Task Description | Task ID | Duration | Dependencies?
Week 7
Owner | Task Description | Task ID | Duration | Dependencies?
Week 8
Owner | Task Description | Task ID | Duration | Dependencies?

## Risk Analysis
Risk Analysis
| RF | Risk | Group Plan for Prevention & Response | Probability | Consequence | Values
1 | 0.98 | Game has to be redesigned (it's not fun) … | [ Type plan here ] | Surprised if it ever happens | Negligible impact to goals. < 2 days | 0.1 to 0.2
|  | Sample Prevention: … |  | Less likely to happen | Minor impact to goals. 3-5 days | 0.3 to 0.4
|  | Sample Responses: ... |  | 50/50 chance | Moderate impact. 1 week | 0.5 to 0.6
2 | 0.93 | Work takes longer than estimated… | [ Type plan here ] | More likely to happen | Major impact. 2 weeks or more | 0.7 to 0.8
|  | Sample Prevention: … |  | Guaranteed to happen | Project Failure | 0.9 to 1.0
|  | Sample Responses: ... |  | Risk | Risk Factor
3 | 0.92 | Difficulty implementing a critical task… | [ Type plan here ] | Planning abandoned under pressure | RF = (0.7 + 0.3) – (0.7 * 0.3) = 0.79
| 0.58 | Sample Prevention: … |  | Acquisition of assets | RF = (0.3 + 0.8) – (0.3 * 0.8) = 0.86
| 0.37 | Sample Responses: ... |  | Work takes longer than estimated | RF = (0.9 + 0.3) – (0.9 * 0.3) = 0.93
4 | 0.86 | Acquisition of assets… | [ Type plan here ] | Game has to be redesigned | RF = (0.9 + 0.8) – (0.9 * 0.8) = 0.98
|  | Sample Prevention: … |  | Lose a team member | Permanent: (0.3 + 0.8) – (0.3 * 0.8) = 0.86
|  | Sample Responses: ... |  |  | Temporary: (0.4 + 0.3) – (0.4 * 0.3) = 0.58
5 | 0.86 | Lose a team member… | [ Type plan here ] | Difficulty implementing a critical task | Lack of skill: (0.2 + 0.9) – (0.2 * 0.9) – 0.92
| 0.58 | Sample Prevention: … |  |  | Tech issue: (0.4 + 0.3) – (0.4 * 0.3) = 0.58
|  | Sample Responses: … |  |  | Feature issue: (0.1 + 0.8) – (0.1 * 0.8) = 0.37
6 | 0.8 | Excessive gold-plating… (polish) | [ Type plan here ] | Excessive gold-plating | RF = (0.5 + 0.6) – (0.5 * 0.6) = 0.80
|  | Sample Prevention: … |  | Temporary burn-out | RF = (0.6 + 0.2) – (0.6 * 0.2) = 0.68
|  | Sample Responses: ... |  | Catastrophic failure | RF = (0.1 + 0.3) – (0.1 * 0.3) = 0.37
7 | 0.79 | Planning abandoned under pressure… | [ Type plan here ]
Sample Prevention: …
Sample Responses: ...
8 | 0.68 | Temporary burn-out… | [ Type plan here ]
Sample Prevention: …
Sample Responses: ...
9 | 0.37 | Catastrophic failure… | [ Type plan here ]
Sample Prevention: …
NO APPLICABLE RESPONSES
Note on C4: It is a challenge to anticipate what features will be fun before having tried them out in their final form.
Note on C5: • Research similar games to determine which features are/are not fun. • Prototype the game elements in a simple digital form to test them. • Design the game around a few simple features, and plan to expand them. • Develop the game in small chunks that allow for frequent feedback.
Note on C6: • Consult a variety of testers to get a consensus about what is not fun. • Make changes based on this consensus and conduct testings session for feedback. • Drop and/or redesign the feature(s).
Note on C7: Programming tasks are remarkably unpredictable; groups have little experience estimating work times.
Note on C8: • Have the Production Plan reviewed by a subject matter expert to ensure the project schedule and scope is realistic. • At each meeting, members will provide a progress update of their tasks; the schedule will be re-addressed to ensure everyone knows the expected timelines.
Note on C9: • Alter deadlines or tasks to accommodate. • Assign another team member to the task. • Consult an expert if lack of skill is the issue.
Note on C10: This can result from lack of programming knowledge/resources, or issues with technology/design.
Note on C11: • Consult with a subject matter expert at the time of the Technical Design Document and/or before the project begins to craft a “development plan” with fewer unknowns. • Research timelines and approaches for each major feature that the team has limited experience implementing.
Note on C12: • Consult with other team members, the lead programmer, and/or a subject matter expert to determine the issue with implementing the feature or technology. • Drop the feature entirely, or restructure it to make it work in/near its current state. • Assign an additional team member to the task, or assign the task to a new member.
Note on C13: Groups often recruit artists from other schools; however, a contingency plan is needed. These “sub-contractors” do not always deliver as promised.
Note on C14: • Address this through game design to align needed assets with the ability and scope of development of the core team. Any assets required from outside the game development team should be non-critical. • If working with an outside artist, keep channels of communication open and plan a weekly meeting and/or progress update.
Note on C15: If it becomes clear that team members lack the skill to complete planned assets or the outside artist will not be delivering the planned assets: • Look into the possibility of purchasing or commissioning the needed art. • Search for royalty-free assets that could fit the needs of the game. • Redesign the art assets to be within the scope of team member skills.
Note on C16: Team members may be temporarily “lost” due to travel plans (such as a wedding). Occasionally, team members will become absent and/or drop out of the project.
Note on C17: • In the game’s design, ensure the scope is flexible or small enough to be supported even if a member leaves. • Establish when any members will be out of town or unavailable up-front, and schedule with attention to those events.
Note on C18: • Redistribute work to other members. • Reevaluate whether all work can be completed, and reschedule as needed. • Add extra hours of required work time, either to the entire team or to the absent member upon their return.
Note on C19: Programmers are often perfectionists, and this can translate into working on tasks beyond what is necessary for it to be complete and functional.
Note on C20: • Specifically establish (in writing) the completion criteria for each assigned task. • Ensure the team understands not to pursue perfection unless no other tasks are outstanding. Once a feature is working, it is complete and a new task should be started.
Note on C21: Other team members should do their best to monitor other tasks. This way, a team member can be told to move on.
Note on C22: Under pressure to deliver critical tasks, accompanying materials to be ignored or sacrificed. Communication may be strained.
Note on C23: It is best to address this issue ahead of time through scheduling. When members are scheduled to work on critical or milestone-based tasks, at least one member will be assigned a less-critical task. This way, there will be at least one member with a clear head.
Note on C24: The member monitoring this risk should either: • Interrupt teammates, if needed, to ensure planning is being addressed; or • Put their non-critical task on hold to shoulder the responsibility of planning.
Note on C25: Groups often log dozens of hours a week this project, along with school and (sometimes) working a job as well.
Note on C26: Each team member should plan their days to include a full night of sleep, and aim for one day “off” a week.
Note on C27: • Redistribute the work to give any “burned-out” members a break. • Plan a fun "team building” activity, like a movie night or online gaming.
Note on C28: Technology is volatile, and even the most careful planning does not always circumvent server crashes or similar issues.
Note on C29: • Set up at least two RAID arrangement backup drives in separate locations (one cloud-based location would suffice). • Arrange to use version control software so members cannot accidentally overwrite each others’ work. This also ensures "roll back" versions will exist.